## AAD Tenants (hidden)
Entity Name | Tenant ID | We "KNOW" they belong to UHG/Optum | Column1 | Notes | Domain Name 1 | Domain Name 2 | Services Running | Global Admin Connection (can be facilitated via Microsoft Support)
4C Medical Group
Advisory Board Company | 3c7ca210-3eae-434f-927c-fa51a7a90475 |  |  | Check with Vijai Rajagopalan | connextionchurch.onmicrosoft.com
advisoryboard734.onmicrosoft.com
| 3fc6d491-8cbb-42d8-91d4-bc313857a9a4 | Maybe |  | Check with Vijai Rajagopalan | advisoryboard429.onmicrosoft.com |  | had a single seat of "Teams" (Free) running
| 12369621-db0d-47d1-932d-c005c11003e4 |  |  | Check with Vijai Rajagopalan | sierrahealth.net
Alere Health | 9d22f3b6-f341-4458-9028-aad885312047 |  |  | Check with Vijai Rajagopalan
American Health Network | a3a84bc9-1b0e-485b-9c84-f7fa540116d22 |  |  | Check with Vijai Rajagopalan |  |  | single seat of O365 Business back a few years ago -(Deprovisioned now)
AppleCare Medical Group
Avella Specialty Pharmacy
Banmedica Chile Clinics | 70071161-3860-4ea1-906c-f5bcf2745635 | Maybe |  | Check with Ryan Finlay | angelakloss.onmicrosoft.com
Banmedica Chile Isapre
Banmedica Colombia Clinics
Banmedica Colombia Colmedica
Banmedica Peru Clinics
DaVita Medical Group | 628d64f0-bdb3-4eb3-b0f5-ae0a7deb757b2 | Probably No |  | Check with Ryan Finlay | davita0.onmicrosoft.com | davita.com | appears to have been a major tenant, but mostly deprovisioned now. Handful of AAD Premium services still running (5) and (1) OneDrive use in January
Diplomat Specialty Pharmacy
Equian | b4860ac0-a8b7-4028-a333-bdfc49ebb37a |  |  | Check with Patrick Conahan | equian2.onmicrosoft.com |  | originally had 500 E3, but deprovisioned in 2017….no active usage.
| 80e8d8ee-c783-427f-b0fc-f8dc3a1938f2 |  | 2232 | Check with Patrick Conahan | equian.com | equian.mail.onmicrosoft.com hcrec.org omniclaim.com fortifiedprovider.com equian.onmicrosoft.com hybrid.equian.com | lots of active servies across O365 and AAD and more.
Executive Health Resources
Genoa Healthcare | 99cb5b04-ca3b-43b9-95d6-036caf5af98d |  |  | Check with Howard Chilcott at Genoa Healthcare
| b1f2a7e7-a518-44f1-8ec1-7d9c0f2a8c591 |  |  | Check with Howard Chilcott at Genoa Healthcare
Genoa Telepsychiatry
hCentive
HealthMarkets | e26173fe-3d73-4419-ac28-b9eda1de24fe |  |  | Check with Ed Larson (from Matt Taylor's team)
| 208984ce-e1ff-49be-b6ca-b7d4aac70f18716 |  |  | Check with Ed Larson (from Matt Taylor's team)
HealthSCOPE
Humedica
Lewin
Logistics Health, Inc. | 6f14c6fd-d007-4d5a-9ce5-97797293a47f1 |  |  | Check with Patrick Conahan
Lusiadas Saude
MARCH Vision Care
MedExpress
MedSynergies
Monarch
N. American Medical Management (CA)
National MedTrans
New West Physicians
Optum Brazil
Optum Workers’ Comp
OptumCare NV
OrthoNet
Peoples Health | 3a90c2c3-6676-449f-967f-0567d58626611 |  |  | Check with Ed Larson (from Matt Taylor's team) | netorgft2050363.onmicrosoft.com
PlusOne
POMCO Group | 510d79ee-6d7d-48a6-bbe8-62bc1fd97cea |  |  | Check with Nick Bohler
ProHEALTH Care (NY)
ProHealth Physicians (CT) | 79e9c2cd-7c7f-4a23-8fae-ac61c3311b2d |  |  | Check with Ryan Finlay
Quality Software Services, Inc.
QualityMetric
Radiation Oncology Center of NV
Rally Health
Reliant Medical Group
Rocky Mountain Health Plan
Savvysherpa
Southwest Medical Associates
Student Resources
Surgical Care Affiliates | Dev/Test -c1abffaf-fc5e-4ed1-9959- d7c44aecf63a
Prod--f0f50638- bede-4f1e-87fc-a1e751da3d74
| 158da037-0c08-42f8-93d2-0a31b1b1f69e |  |  | Check with Ryan Finlay | optumcare.onmicrosoft.com
The Everett Clinic | 2daeffa1-49c1-4871-b5cf-dada561ce9d1 |  | 1711 | Check with Phoebe Egan Sodman (Matt Taylor's team)
The Polyclinic
UHG Brazil (AMIL)
UnitedHealthcare Nevada Market
USHEALTH Group
USMD Health System
Vivify Health
WellMed | ac02efaa-7bff-4fee-9e7b-b0a6f6271fc4 |  |  | Check with Ryan Finlay
| db25ec4e-7739-4d88-a552-43fc752b1510 |  |  | Check with Ryan Finlay
| 307cd75d-d0e9-42a8-bdfc-f0c01ab16282 |  |  | Check with Ryan Finlay
| 5e8998e8-b29d-440c-818a-5a051d0282d01 |  |  | Check with Ryan Finlay
Westmed Practice Partners | 6453edc5-8deb-4328-8f14-fe9d8b13ea99 |  |  | Check with Patrick Conahan | wellmed.net
Others:
OptumConnect
PatientLikeMe
Insipiris - AA
OptumRx
UHG (NEW since February) (appears to be primary) | db05faca-c82a-4b9d-b9c5-0f64b6755421 | Optum Owned, LP applied |  | Jason - Optum Owned and Launchpad applied
OptumCare | 85f46a4d-265f-41b9-aaef-c494b7617e7f | Optum Owned, LP applied |  | Jason - Optum Owned and Launchpad applied | uhgazure.onmicrosoft.com
NEW UHSWEB.COM | f972c0cf-85cf-4203-8599-eb90be9f6604 |  |  | Unknown | scasurgery.onmicrosoft.com
(NEW) DSISTG | 06445236-3ac4-4dc4-a102-0f77576da83f | Optum Owned, LP applied |  | Jason - Optum Owned and Launchpad applied | uhsweb.com
(NEW) Unified HealthNet | 1265628f-bc0f-424c-b17e-09da9ddfe688 |  |  | Unknown | dsistg.onmicrosoft.com
(NEW) Oxford HealthCare | ec379365-2aaf-440f-8f6c-f6471d45d8c9 |  |  | Unknown | unifiedhealthnet.onmicrosoft.com
(NEW) Connextion Church | e57d871e-0568-4d72-85ee-b5d522830792 |  |  | Unknown | oxfordhealthcare232.onmicrosoft.com
UNITED HEALTH SERVICES | 88675a7a-8872-4d2c-ad25-afdab97c2e62 |  |  | Unknown
UNITED HEALTH SERVICES | 238e1eeb-b5d2-4f3c-995c-5673e24f9bd6291 |  |  | Unknown
USLEWINCOLLABSVCS | 964e8412-235a-48e4-b8ed-1c00e98147f826 | Optum Owned, LP applied |  | Jason - Optum Owned and Launchpad applied

## Dashboard
Program Titan | [9 empty] | Overall - In Progress | [5 empty] | Overall Status |  | Overall In Progress / Delayed |  | Overall In Progress / Delayed |  | Overall In Progress / Delayed |  | Overall In Progress / Delayed |  | Overall In Progress / Delayed |  | Overall Status Priority 1 & 2 |  | Cloud Provider Count - In Scope not Complete
Public Cloud Migration | [10 empty] | In Progress | Delayed | [5 empty] | Overall Status | (Multiple Items) | Overall Status | (Multiple Items) | Overall Status | (Multiple Items) | Overall Status | (Multiple Items) | Overall Status | (Multiple Items) | Priority | (Multiple Items) | Overall Status | (Multiple Items) | Entity Name | (Multiple Items)
Dashboard | [9 empty] | Validation | 0 | 0
[10 empty] | Presentation | 5 | 5 |  |  |  | Row Labels | Count of Overall Status | Row Labels | Count of Validation | Row Labels | Count of Presentation | Row Labels | Count of Questionnaire | Row Labels | Count of ASKID/GL | Row Labels | Count of Migration | Row Labels | Count of Overall Status | Row Labels | Count of Provider | Count of Entity Name
[10 empty] | Questionnaire | 3 | 0 |  |  |  | Delayed | 2 | Complete | 20 | 0 | 1 | 0 | 7 | 0 | 8 | 0 | 9 | Delayed | 2 | 0 | 9 | 66
[10 empty] | ASKID/GL | 0 | 0 |  |  |  | In Progress | 18 | Grand Total | 20 | Complete | 12 | Complete | 12 | Complete | 11 | In Progress | 11 | In Progress | 12 | AWS | 10
[10 empty] | Migration | 1 | 3 |  |  |  | No Cloud Workloads | 31 |  |  | Delayed | 2 | In Progress | 1 | In Progress | 1 | Grand Total | 20 | No Cloud Workloads | 13 | Azure | 7
[10 empty] | Total | 9 | 8 |  |  |  | Not Started | 8 |  |  | In Progress | 5 | Grand Total | 20 | Grand Total | 20 |  |  | Complete | 3 | Google | 2
[10 empty] | Cloud Providers - In Scope / Less than Complete | [5 empty] | Complete | 12 |  |  | Grand Total | 20 | [6 empty] | Grand Total | 30 | Grand Total | 28
[10 empty] | AWS | Azure | Google |  |  |  | #N/A | 4
[10 empty] | 10 | 7 | 2 |  |  |  | Grand Total | 75
Entity Name | LOB | Priority | Provider | Overall Status | Validation | Presentation | Questionnaire | ASKID/GL | Migration | LaunchPad | Remediation | EIS Endorsement | O365 Migration | Decommission | Notes
Advisory Board Company | OptumInsight |  | AWS | In Progress | Complete | Complete | Complete | Complete | complete | complete | Complete | In Progress | 0 | 0 | 0
Alere Health | UHC Global | 0 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
American Health Network | OptumHealth - Care Delivery | 2 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress | 0 | O365 migration expects to complete by End of January
ApertureCVO | OptumHealth - Care Delivery | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
AppleCare Medical Group | OptumHealth - Care Delivery | 2 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress | 0 | O365 migration expects to complete by End of January
Avella Specialty Pharmacy | Optum Rx | 0 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Banmedica Chile Clinics | UHC Global | 0 | 0 | Not Started | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Banmedica Chile Isapre | UHC Global | 0 | 0 | Not Started | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Banmedica Colombia Clinics | UHC Global | 0 | 0 | Not Started | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Banmedica Colombia Colmedica | UHC Global | 0 | 0 | Not Started | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Banmedica Peru Clinics | UHC Global | 0 | 0 | Not Started | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DaVita Medical Group | OptumHealth - Care Delivery | 2 | Azure | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | 0 | Complete | Complete | Complete
Diplomat Specialty Pharmacy - CastiaRx | Optum Rx | 1 | AWS | In Progress | Complete | Complete | Complete | Complete | Complete | Complete | Complete | In Progress | Not in Scope | 0
Diplomat Specialty Pharmacy - Envoy Health | Optum Rx | 1 | Azure | In Progress | Complete | Complete | Complete | Complete | In Progress | 0 | 0 |  | Not in Scope | 0
Diplomat Specialty Pharmacy (DSP) | Optum Rx | 1 | AWS | In Progress | Complete | Complete | Complete | Complete | Complete | Complete | In Progress |  | Not in Scope | 0
Equian - AWS | OptumInsight | 1 | AWS | In Progress | Complete | Complete | Complete | Complete | Complete | Complete | In Progress |  | Not in Scope | 0
Equian - Azure | OptumInsight | 1 | Azure | In Progress | Complete | Complete | Complete | Complete | Complete | Complete | In Progress |  | Not in Scope | 0
Equian - Google | OptumInsight | 1 | Google | No Cloud Workloads | Complete | Complete | 0 | 0 | 0 | 0 | 0 | 0 | Not in Scope | 0
Executive Health Resources | OptumInsight | 0 | 0 | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | 0 | 0 | 0 | 9/18 - Awaiing follow-up to ClearData discussions
Genoa Healthcare - AWS | Optum Rx | 1 | AWS | In Progress | Complete | Complete | Complete | Complete |  | 0 | 0 | 0 | 0 | 0
Genoa Healthcare - Azure | Optum Rx | 1 | Azure | In Progress | Complete | Complete | Complete | Complete |  | 0 | 0 | 0 | 0 | 0
Genoa Telepsychiatry - AWS | OptumHealth | 0 | AWS | Complete | Complete | Complete | Complete | Complete | Complete | Complete | 0 | 0 | 0 | 0 | 9/21 - Meeting with Tedd Mendes to walk through process for Cloud discovery
Genoa Telepsychiatry - Google | OptumHealth | 0 | Google | Complete | Complete | Complete | Complete | Complete | Complete |  | 0 | 0 | 0 | 0 | 9/21 - Meeting with Tedd Mendes to walk through process for Cloud discovery
hCentive | OptumInsight | 0 | AWS | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | 0 | 0 | 0 | 9/21 - Meeting with Tedd Mendes to walk through process for Cloud discovery
HealthMarkets | UHC E&I | 0 | AWS | In Progress | Complete | Complete | Complete | In Progress | 0 | 0 | 0 | 0 | 0 | 0
HealthSCOPE | UHC E&I | 0 | AWS | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Humedica | OptumInsight | 0 | AWS | Complete | Complete | Complete | Complete | Complete | Validating | 0 | 0 | 0 | 0 | 0 | 0
Insipiris - AA | OptumInsight | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Lewin | OptumInsight | 0 | Azure | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Logistics Health, Inc. | OptumInsight | 0 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lusiadas Saude | UHC Global | 0 | 0 | Not Started | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MARCH Vision Care | UHC E&I | 0 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MedExpress | OptumHealth - Care Delivery | 2 | AWS | In Progress | Complete | Complete | Complete | Complete | In Progress | 0 | 0 | 0 | In Progress | 0 | O365 Migration - Plan to finish by end of January/21
MedSynergies | OptumInsight | 0 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Moment Health | OptumInsight | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Monarch | OptumHealth - Care Delivery | 2 | Azure | Complete | Complete | Complete | Complete | Complete | Complete | Complete | 0 | 0 | In Progress | 0 | O365 Migration - Tentative completion end of March/21
N. American Medical Management (CA) | OptumHealth - Care Delivery | 2 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O365 Migration - Tentaive start of 2/21
National MedTrans | UHC E&I | 0 | AWS | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | 0 | 0 | 0 | 0
New West Physicians | OptumHealth - Care Delivery | 2 | Azure | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | 0 | Complete | 0 | 0
Optum Brazil | Optum International | 0 | 0 | Not Started | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Optum Workers’ Comp | Optum Rx | 0 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OptumCare NV - 4C Medical Group | OptumHealth - Care Delivery | 2 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OptumCare NV - Radiation Oncology of NV (USONV) | OptumHealth - Care Delivery | 2 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OptumCare NV - Southwest Medical Associates | OptumHealth - Care Delivery | 2 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OrthoNet | Optum Consumer Solutions | 0 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PatientLikeMe | Optum Consumer Solutions | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
Peoples Health | UHC M&R | 0 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PlusOne | Optum Consumer Solutions | 0 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
POMCO Group | UHC E&I | 0 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ProHEALTH Care (NY) | OptumHealth - Care Delivery | 2 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Started | 0 | O365 Migration - Planned for 2/26 start
ProHealth Physicians (CT) | OptumHealth - Care Delivery | 2 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In Progress | 0 | O365 Migration - Tentaive start of 3/21
Quality Software Services, Inc. |  | 0 | 0 | In Progress | Complete |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
QualityMetric | OptumInsight | 0 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Radiation Oncology Center of NV | OptumHealth - Care Delivery | 0 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Started | 0 | 0
Rally Health | Optum Consumer Solutions | 1 | AWS | In Progress | Complete | Complete | Complete | In Progress | 0 | 0 | 0 | 0 | Not in Scope | 0
Reliant Medical Group | OptumHealth - Care Delivery | 2 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Started | 0 | O365 Migration - Tentative completion end of Feb/21
Rocky Mountain Health Plan | UHC C&S | 0 | Azure | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | 0 | 0 | 0 | 9/21 - Meeting with Tedd Mendes to walk through process for Cloud discovery
UHG R&D - AWS | UHC Global | 1 | AWS | In Progress | Complete | Complete | In Progress | In Progress | Delayed | 0 | 0 | 0 | Not in Scope | 0
UHG R&D - Azure | UHC Global | 1 | Azure | In Progress | Complete | Complete | In Progress | In Progress | Delayed | 0 | 0 | 0 | Not in Scope | 0
UHG R&D - Google | UHC Global | 1 | Google | In Progress | Complete | Complete | In Progress | In Progress | Delayed | 0 | 0 | 0 | Not in Scope | 0
Southwest Medical Associates | OptumHealth - Care Delivery | 0 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not in Scope | 0
Student Resources | UHC E&I | 0 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Surgical Care Affiliates - AWS | OptumHealth - Care Delivery | 0 | AWS | In Progress | Complete | Complete | Complete | Complete | Complete | In Progress |  |  | 0 | 0 | 0
Surgical Care Affiliates - Azure | OptumHealth - Care Delivery | 0 | Azure | No Cloud Workloads | Complete | Complete | Complete | Complete | In Progress | 0 | 0 |  | 0 | 0 | 0
TEC - Northwest Physicians Network | OptumHealth - Care Delivery | 1 | Azure | In Progress | Complete | Complete | Complete | Complete | In Progress | 0 | 0 | 0 | Not Started | 0
TEC - The Everett Clinic | OptumHealth - Care Delivery | 1 | Azure | No Cloud Workloads | Complete | Complete | Complete | Complete | In Progress | 0 | 0 | 0 | Not Started | 0 | 0
TEC - The Polyclinic | OptumHealth - Care Delivery | 1 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Started | 0 | 0
UHG Brazil (AMIL) | UHC Global | 0 | 0 | Not Started | Not Started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
UnitedHealthcare Nevada Market | UHC E&I | 0 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
USHEALTH Group | UHC E&I | 0 | Azure | In Progress | Complete | Complete | Complete | Complete | In Progress | 0 | 0 | 0 | Not Started | 0 | 0
USMD Health System | OptumHealth - Care Delivery | 2 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Complete | 0 | 0
Vivify Health - AWS | OptumHealth - Care Delivery | 0 | AWS | In Progress | Complete | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vivify Health - Azure | 0 | 0 | Azure | In Progress | Complete | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WellMed | 0 | 2 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | In progress | 0 | O365 Migration - Migration on hold
Westmed Practice Partners | OptumInsight | 0 | 0 | No Cloud Workloads | Complete | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## MASTER
Entity |  |  | Contacts |  |  |  | Status | [9 empty] | Discovery | [7 empty] | Notes |  | Dashboard Data
Entity Name | Segment | LOB | CRIS LOB Executive | CRIS Engagement Manager | CRIS Integration Program Lead | Key Contacts | Priority | Discovey Required | CRIS Discovery Start Date | CRIS Discovery End Date | CRIS Discovery % Complete | Cloud Overview (Deck) | ASKID/GL Status | HCC Ready | LaunchPad 2 | Remediation 2 | Public Cloud (Y/N) | Public Cloud Vendor(s) | UHG MSA / ISA Status | ASK ID / GL Code | Avg Monthly Spend | 3rd Party Vendor (Y/N) | 3rd Party Comments | Accounts | Comments | Done/Removed | Overall Status | Validation | Presentation | Questionnaire | ASKID/GL | Migration | LaunchPad | Remediation | EIS Endorsement | O365 Migration | Decommission | Dashboard Notes | Column1
Advisory Board Company | Optum | OptumInsight | Angela Thorpe | Ann Gerity |  | ATTN: Debra Flaherty awsabcmaster@advisory.com eTechAdmin <eTechAdmin@advisory.com> 7/16 new contact - Wyatt Anderson |  | Yes | 779247480178 | Completed | 100% |  |  | Yes |  |  | Y | AWS | In Progress | UHGWM110-025556 UHGWM110-026687 | 6000 |  |  | 779247480178 ($60) - Payer 278151539847 ($100) - Optum Dev 328905000296 ($500) - Etech Dev 345616689425 ($4k) - ABC Mgmt 448621400967 ($1) - Advisory Board 460791684257 ($1k) - ABC Security 546140078785 ($300) - Research Prod 637475421529 ($50) - Kevin Barnes 857642938110 ($150) - Etech Prod | 9/9 AG - call scheduled for 9/15 to review status provided by Paul Towers (below). We still have a number of AWS accounts that have not been moved over to Optum master billing. I am planning to get it done by the end of this year. Here are the accounts and status. 779247480178 – Payer (abcmaster) • Terminate once all of the below accounts have moved to Optum master billing or have been deleted. Q4 2020 345616689425 – AWS ABC Mgmt (abcmgmt) • Move early Q4 2020 546140078785 – Optum Research Production (optumresearchprod) • MOVE COMPLETED - 10/8 460791684257 – AWS ABC Security • Terminate mid Q4 2020 328905000296 – AWS ETECH Dev • Terminate mid Q4 2020 Found though invoice email: AWS: ****0029 - $103.68/mo - brennemk@advisory.com AWS: ****3542 - $1.21/mo - mathewsj@advisory.com 7/16 PJC - per Jason moved some and decom'd some. Still need to find out remaining to move or decom (whats left) 7/23 AG - migration completed, clean up & decom to be completed |  | In Progress | Complete | Complete | Complete | Complete | complete | complete | Complete
Alere Health | Optum | UHC Global | Thomas Morning | N/A | Thomas Morning | [11 empty] | N | [7 empty] | 8/27: TT - There is no cloud spend for Alere Health, per Thomas Morning |  | No Cloud Workloads | Complete
American Health Network | Optum | OptumHealth - Care Delivery | Tony Kranz, Alan Kroth | Joanne Castillo | Farhan MO | Marty Zoiss | 2 | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N |  | N/A | N/A | N/A | N/A | N/A | N/A | 7/17/20 Jason W. - Per Marty Zoiss, no public cloud | Y | No Cloud Workloads | Complete | [7 empty] | In Progress
AppleCare Medical Group | Optum | OptumHealth - Care Delivery | Tony Kranz, Alan Kroth | Joanne Castillo | Carly Glieden | Amber Senteno, Jon Seung | 2 | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N |  | N/A | N/A | N/A | N/A | N/A | N/A | 8/3 JAC - Per Alan Kroth (as per business partner), no public cloud presence. | Y | No Cloud Workloads | Complete | [7 empty] | In Progress
Avella Specialty Pharmacy | Optum | Optum Rx | Angela Thorpe | Chris Bongartz | none | AWS: Angela Tarango Azure : Donna Zapata |  |  | 2020-08-25 | 2020-08-25 | 100 | N/A | N/A | N/A | N/A | N/A | N |  | N/A | N/A | N/A | N/A | N/A | N/A | 08/25/20 -Jason W. - Per Corey Carlson, nothing currently hosted in Azure or AWS Atia 2/14 - Jason you may want to reach out to EIS TISA Enright, Patrick J <Patrick.Enright@optum.com> 2/3 - Jason - Email sent to Angela asking what assistance is needed to get account closed. 2/3 - Jason - Email sent to Donna asking on the Azure tenant/sub 12/11 - Jason/Email sent to Donna asking what is hosted our in Azure for Avella. 12/11 - Angela reports that account is no longer needed. |  | No Cloud Workloads | Complete
Banmedica Chile Clinics | UHC | UHC Global | Thomas Morning | N/A | Thomas Morning | [11 empty] | TBD | [9 empty] | Not Started | Not Started | [9 empty] | Evaluating international regulations, effort, timing, and impact
Banmedica Chile Isapre | UHC | UHC Global | Thomas Morning | N/A | Thomas Morning | [11 empty] | TBD | [9 empty] | Not Started | Not Started | [9 empty] | Evaluating international regulations, effort, timing, and impact
Banmedica Colombia Clinics | UHC | UHC Global | Thomas Morning | N/A | Thomas Morning | [11 empty] | TBD | [9 empty] | Not Started | Not Started | [9 empty] | Evaluating international regulations, effort, timing, and impact
Banmedica Colombia Colmedica | UHC | UHC Global | Thomas Morning | N/A | Thomas Morning | [11 empty] | TBD | [9 empty] | Not Started | Not Started | [9 empty] | Evaluating international regulations, effort, timing, and impact
Banmedica Peru Clinics | UHC | UHC Global | Thomas Morning | N/A | Thomas Morning | [11 empty] | TBD | [9 empty] | Not Started | Not Started | [9 empty] | Evaluating international regulations, effort, timing, and impact
DaVita Medical Group | Optum | OptumHealth - Care Delivery | Tony Kranz, Alan Kroth | Joanne Castillo | Annaliese Reutemann | Bryan Nieznajko | 2 | No | 2020-07-17 | Complete 8/3/2020 | 100% | N/A | N/A | Yes |  |  | Y | Azure |  | UHGWM110-025713 |  |  |  |  | 9/2 JAW - Bryan N will send over contacts to verify no other subscriptions/accounts exist - confirming decom phase 8/3 JAC - Per Bryan Nieznajko, 2 subsciptions processed through standard intake for HCC (net new). No other apps in the cloud. 7/21 JAC - Per Bryan Nieznajko/OCIO, Prod and Non-Prod subscription. Meeting with Bryan 7/29 for next steps. | Y | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete |  | Complete | Complete
Diplomat Specialty Pharmacy - CastiaRx | Optum | Optum Rx | Angela Thorpe | Chris Bongartz | Aric Fier | Steven Bellistri (technical) sbellistri@castiarx.com Kevin Mangin (financial) kmangin@castiarx.com | 1 |  | 2020-07-23 | [7 empty] | Y | AWS |  | UHGWM110-026954 |  |  |  |  | 12/7/2020-Jason L. HCC sent email out asking for a date next week to schecule the 10/27/20 -Jason L. HCC intial meeting completed and notes sent out. Scheduling account move . 10/11/20 -Jason W. questionnaire completed. 09/29/20 - Jason W. Scheduled questionnaire review call for 9/6/20. Per EIS: Cloud de-prioritized due to resource constraints and security tasks taking priority |  | In Progress | Complete | Complete | Complete | Complete | Complete | Complete | In Progress | In Progress | Not in Scope |  | 9/18 - meeting scheduled for 9/23 to start ISA process Per EIS: Cloud de-prioritized due to resource constraints and security tasks taking priority
Diplomat Specialty Pharmacy - Envoy Health | Optum | Optum Rx | Angela Thorpe | Chris Bongartz | Aric Fier | Bob Van Gessel rvangessel@diplomat.is Natasha Mayfield nmayfield@envoyhealth.is Daniel Schmidt DSchmidt@diplomat.is Joe Hunsinger jhunsinger@diplomat.is | 1 |  | 2020-07-23 | [7 empty] | Y | Azure |  | UHGWM110-026339 |  |  |  |  | 2/1: O365 primary reason for tenant. There is a subscription however the plan is to move the funcationality running in the sub to diplomats datacenter. Will know more on a timeline by mid to end of Feburary. Follow back up with Joe and Ben. 1/27: Meeting scheduled to align tasks 12/15: LaunchPad ticket created to resolve issues with migrating Azure. Launchpad has move resolution to Q1,2021 10/26/20 -Jason L. completed intial HCC meeting to provide information on Tenant and subscirption move. Sent email with details of restrictive policies that will be applied. 10/11/20 -Jason W. questionnaire completed. 09/29/20 - Jason W. Scheduled questionnaire review call for 9/6/20. Per EIS: Cloud de-prioritized due to resource constraints and security tasks taking priority Jason W 08/20/20 -- discussed with Colm, he's providing ASK IDs and questionnaire response for "tuck ins" inclduing Envoy -- followup call scheduled for 8/24 PJC 7/23 - Reviewed the deck w/Chad Mines & Chris Bongartz. Believe there is only a O365 presence. Chris and Jeff G to discuss more. JAW 8/5 - Tuck under entities; CastiaRx, DSP, Envoy Health under DSP CastiaRx = AWS (need ISA to moved forward), DSP via 3rd party Glacier = AWS, Envoy Health = Azure portal (mostly SQL) with 3rd party Move forward with CastiaRx - need ISA (Alex J, CRIS) Investigate SHI relationship (Diplomat team) |  | In Progress | Complete | Complete | Complete | Complete | In Progress |  |  | In Progress | Not in Scope |  | 2/1- Envoy Health is moving workload to on-prem in 2021 (when DC is trusted) 1/27: Meeting scheduled to align tasks Per EIS: Cloud de-prioritized due to resource constraints and security tasks taking priority
Diplomat Specialty Pharmacy (DSP) | Optum | Optum Rx | Angela Thorpe | Chris Bongartz | Aric Fier | Bob Van Gessel rvangessel@diplomat.is Ben Thompson bthompson@diplomat.is Daniel Schmidt DSchmidt@diplomat.is | 1 |  | 2020-07-23 |  |  | Complete 7/23/2020 |  | No |  |  | Y | AWS | Need for CastiaRx | UHGWM110-026677 |  | Y | DSP - via SHI Envoy Health - Need more info |  | 1/27: Scheduled meeting to discuss SHI contract 12/15 DSP will submit request to cancel contract with SHI. It will cancel 30 days later 10/11/20 -Jason W. questionnaire completed. 09/29/20 - Jason W. Scheduled questionnaire review call for 9/6/20. Per EIS: Cloud de-prioritized due to resource constraints and security tasks taking priority Jason W 08/20/20 -- discussed with Colm, he's providing ASK IDs and questionnaire response for "tuck ins" inclduing Envoy -- followup call scheduled for 8/24 PJC 7/23 - Reviewed the deck w/Chad Mines & Chris Bongartz. Believe there is only a O365 presence. Chris and Jeff G to discuss more. JAW 8/5 - Tuck under entities; CastiaRx, DSP, Envoy Health under DSP CastiaRx = AWS (need ISA to moved forward), DSP via 3rd party Glacier = AWS, Envoy Health = Azure portal (mostly SQL) with 3rd party Move forward with CastiaRx - need ISA (Alex J, CRIS) Investigate SHI relationship (Diplomat team) |  | In Progress | Complete | Complete | Complete | Complete | Complete | Complete | In Progress | In Progress | Not in Scope |  | 2/5 - account moved over under Optum Master and lauchpad successfully applied 2/1 - account should be moved to UHG agreement in the next week. 1/27: Scheduled meeting to discuss SHI contract 9/18 - awaiting security work to free up resources Per EIS: Cloud de-prioritized due to resource constraints and security tasks taking priority
Equian - AWS | Optum | OptumInsight | Angela Thorpe | Ann Gerity | Kevin Joslyn | Phabenstein@equian.com | 1 |  | 2020-07-01 |  | 25% | Scheduled for 8/7 |  | Yes | Yes | In Progress | Y | AWS |  | 41322-06990-USAMN101-821003 | 99872 |  |  |  | 11/20 - The two main Equian AWS were moved over into Optum Central mgmt and Launchpad was applied. Remdication of security vul is in progress. The 3rd AWS account is not in use and is in process of being decomissioned. 10/12 meeting 3 AWS accounts 2 accounts managed by SHI - Omni and subropoint. These accounts are about 50k each. 1 account is pay as you go, ~150 per month Next steps are a meeting with Equian finance and tech team. 8/25 AG: Equian resources are focusing on the migration to the RNH, efforts can begin once the team has cycles available. 8/18 AG - deck walk through completed, Jason L. indicated no additonal documentation needs to be completed. There is third party involvement in cloud account, Equain will come back to begin integration planning/execution when they have a timeline to remove party from account. 7/23 AG - discovery started, deck walk through scheduled for 8/7 |  | In Progress | Complete | Complete | Complete | Complete | Complete | Complete | In Progress |  | Not in Scope |  | 9/18 - awaiting security work to free up resources RNH migration taking priority for Equian resources
Equian - Azure | Optum | OptumInsight | Angela Thorpe | Ann Gerity | Kevin Joslyn | Phabenstein@equian.com | 1 |  | 2020-07-01 |  | 25% | Scheduled for 8/7 |  | No |  |  | Y | Azure |  | 41322-06990-USAMN101-821003 | 99872 |  |  |  | 10/12 meeting 2 Azure AD tenants -Equian main tenant is used for O365 only, no Azure subscription -DevOps tenant has a workload that is believed to not be used. Jonathan is researching if sub and tenant can be closed. 8/25 AG: Equian resources are focusing on the migration to the RNH, efforts can begin once the team has cycles available. 8/18 AG - deck walk through completed, Jason L. indicated no additonal documentation needs to be completed. There is third party involvement in cloud account, Equain will come back to begin integration planning/execution when they have a timeline to remove party from account. 7/23 AG - discovery started, deck walk through scheduled for 8/7 |  | No Cloud Workloads | Complete | Complete | Complete | Complete | Complete | Complete | In Progress |  | Not in Scope |  | 9/18 - awaiting security work to free up resources RNH migration taking priority for Equian resources
Equian - Google | Optum | OptumInsight | Angela Thorpe | Ann Gerity | Kevin Joslyn | Phabenstein@equian.com | 1 |  | 2020-07-01 |  | 25% | Scheduled for 8/7 |  | No |  |  | Y | Google |  | 41322-06990-USAMN101-821003 | 99872 |  |  |  | 12/12 meeting No GCP is known, Jonathan will be validating. 8/25 AG: Equian resources are focusing on the migration to the RNH, efforts can begin once the team has cycles available. 8/18 AG - deck walk through completed, Jason L. indicated no additonal documentation needs to be completed. There is third party involvement in cloud account, Equain will come back to begin integration planning/execution when they have a timeline to remove party from account. 7/23 AG - discovery started, deck walk through scheduled for 8/7 |  | No Cloud Workloads | Complete | Complete | [6 empty] | Not in Scope |  | 9/18 - awaiting security work to free up resources RNH migration taking priority for Equian resources
Executive Health Resources | Optum | OptumInsight | Angela Thorpe | Ann Gerity |  | Michael Flail |  |  | 2020-07-23 |  |  |  |  | No |  |  | TBD | [7 empty] | 9/10 update: call held with EHR team, only app hosted in cloud provisioned under UHG account. UHGWM110-020624¦OPAS_Case_advisor_Prod¦Microsoft¦AZU_P0001496¦6531c445-10ec-4f00-84d5-fc0ae4f54cd2 9/9 AG - EHR has a product hosted in Azure, discovery call scheduled for 9/10 with Jeff W's team 9/8 AG - update from Andrew Lexa: EHR was integrated on the Optum network in 2015 and we were part of the corporate rollout of Office365. The EHR Systems team manages all applications and customer web portals internally with no public or third party providers. We have a new product called Case Advisor that is hosted in Azure. Karunesh Kumar would be able to provide more details on this application. 9/8 AG - Michael Flail confirmed they are using O365, on prem. Andrew Lexa was identifed as the point of contact for other cloud related questions. Confirmation of cloud presence pending. 8/25 - have reached out to Michael Flail @ the BP, OOO until 8/26 (no backup identifed, try to get alternate name) 8/7/23 AG - identifed point of contact, enagaged for status |  | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
Genoa Healthcare - AWS | Optum | Optum Rx | Angela Thorpe | Chris Bongartz | N/A | colm_hasson@optum.com McConnell, John [From Genoa] <JMcconnell@genoahealthcare.com> Raustein, Peter [From Genoa] <praustein@genoahealthcare.com> | 1 |  | 2020-08-25 |  | 10 | Complete 7/23/2020 |  | Blocked | Blocked | Blocked | Y | AWS |  |  | 200000 | Y | ClearData |  | 1/5/21: Genoa currently leverages ClearData to manage their infrastructure in Amazon Web Services (AWS). The current technology in AWS will be moved to the Optum Health Care Cloud (HCC) AWS solutions when the current agreement expires on 9/7/2021 08/25/20 - Jason W. - Per Aric Fier, can send over questionnaire but will hold off any dicussion for at least two week. There are 60 to 100 VMs in AWS but leadership is discussing options with agreement with ClearData JL 6/30 - Alex and Jason meet with Genoa, the focus was on cost to migrate. Clear data owns the accounts and Genoa will need to migrate the workloads off of the current account into a new account. Alex had several meetings with Genoa, they do not want to move due to cost.**This is what they pay to ClearDATA, a 3rd party vendor who performs work on their two AWS accounts.Jeff: sent note to Francois to inquire.PJC 7/23 - Reviewed the deck w/Chad Mines & Chris Bongartz. JJG 7/30 - Leadership mtgs with CIO/CEO - no action to take yet. |  | In Progress | Complete | Complete | Complete | Complete | [6 empty] | 9/18 - Awaiiting follow-up to ClearData discussions Per Aric Fier, pause for at least two week. Leadership discussing options with ClearData agreement
Genoa Healthcare - Azure | Optum | Optum Rx | Angela Thorpe | Chris Bongartz | N/A | colm_hasson@optum.com McConnell, John [From Genoa] <JMcconnell@genoahealthcare.com> Raustein, Peter [From Genoa] <praustein@genoahealthcare.com> | 1 |  | 2020-08-25 |  | 25 | Complete 9/30/2020 |  | Blocked | Blocked | Blocked | Y | Azure |  |  | 200000 | Y | ClearData |  | 08/25/20 - Jason W. - Per Aric Fier, can send over questionnaire but will hold off any dicussion for at least two week. There are 60 to 100 VMs in AWS but leadership is discussing options with agreement with ClearData JL 6/30 - Alex and Jason meet with Genoa, the focus was on cost to migrate. Clear data owns the accounts and Genoa will need to migrate the workloads off of the current account into a new account. Alex had several meetings with Genoa, they do not want to move due to cost. **This is what they pay to ClearDATA, a 3rd party vendor who performs work on their two AWS accounts. Jeff: sent note to Francois to inquire. PJC 7/23 - Reviewed the deck w/Chad Mines & Chris Bongartz. JJG 7/30 - Leadership mtgs with CIO/CEO - no action to take yet. |  | In Progress | Complete | Complete | Complete | Complete | [6 empty] | 9/18 - Awaiiting follow-up to ClearData discussions Per Aric Fier, pause for at least two week. Leadership discussing options with ClearData agreement
Genoa Telepsychiatry - AWS | Optum | OptumHealth | Tony Kranz, Alan Kroth | Joanne Castillo | Ashish Palia | IT manager: Alex Aronson alex.a@genoatelepsychiatry.com HR Lead- Christine Staub cstaub@genoatelepsychiatry.com |  |  | 2020-06-15 | Complete 6/19/2020 | 100 | N/A | Complete | Yes | Scheduling migration for AWS |  | Y | AWS | N/A | UHGWM110-018809 | 900 |  |  | 120743116205 | 1/5/21:Genoa currently leverages ClearData to manage their infrastructure in Amazon Web Services (AWS). The current technology in AWS will be moved to the Optum Health Care Cloud (HCC) AWS solutions when the current agreement expires on 9/7/2021 JG: Being worked outside of TitanJL 6/30 - Jena worked with AE to get ASK ID created and GL mapped. Jena working on schecuedling migration. Google workload is Gsuite only.AWS account will need to move over.This account/workload moved to another part of the business. Still needs move, but would be separate from below.Also has a GCP workload (per Kevin Wright).7/16 PJC - actively migrating AWS per JL. G suite not inscope of cloud track - need to communicate to Collab track to Office/O365 complete migration |  | Complete | Complete | Complete | Complete | Complete | Complete | Complete
Genoa Telepsychiatry - Google | Optum | OptumHealth | Tony Kranz, Alan Kroth | Joanne Castillo | Ashish Palia | IT manager: Alex Aronson alex.a@genoatelepsychiatry.com HR Lead- Christine Staub cstaub@genoatelepsychiatry.com |  |  | 2020-06-15 | Complete 6/19/2020 | 100 | N/A | Complete | Yes | Scheduling migration for AWS |  | Y | Google | N/A | UHGWM110-018809 | 900 |  |  | 120743116205 | JG: Being worked outside of Titan JL 6/30 - Jena worked with AE to get ASK ID created and GL mapped. Jena working on schecuedling migration. Google workload is Gsuite only. AWS account will need to move over. This account/workload moved to another part of the business. Still needs move, but would be separate from below. Also has a GCP workload (per Kevin Wright). 7/16 PJC - actively migrating AWS per JL. G suite not inscope of cloud track - need to communicate to Collab track to Office/O365 complete migration |  | Complete | Complete | Complete | Complete | Complete | In Progress
hCentive | Optum | OptumInsight | Angela Thorpe | Ann Gerity | Ashish Palia | Chris Dellinger (POC) + Kunal from his team Rohit Dhodi (Security) |  | No | Started | Completed | 100% | NA |  | Yes | Complete w/ Findings |  | Y | AWS | Complete (Non-Prod) | GL: 41325-06333-820105 | $50K-60K |  |  | NP: 504357334963 (RIs- moving) P: 184947885659 (not yet moving) Gov: 207460668013 (not in use, to decommission.) 2770...gmail account, Not in use, need to decommission. | 7/23 AG - Chris Delliger confirmed hCentive AWS account migrated to Optum back in May AWS Org Migration scheduled 4/30 4/6- Reseller Notification of migration 4/30. Reviewing tech needs for migration 4/9. 3/24- AWS reseller needs 30 day notification. Chris attempting to establish timeline 3/11- Intake form completed- RITM10103000 2/25- still waiting on ASK filed 2/12. 2/10- GL recieved. Need Employee Account owner. 1/24- Jason to work with Chris on Legal, Jena to assist with ASK ID. Chris sending emails with info 1/22 - Meeting scheduled for 1/24 to talk through and begin the process. 11/26- Name change issue. Email sent 12/16 for update Jeff: ES&P & AWS follow-up. (3% discount via Engineering AI (India)) Jeff: Redbox introduction once we're there. Jeff sent email to Chris re: ASKID/GL. ASK ID: UHGWM110-025505 Account request number: RITM1010300 Note: Question for Chris, where the RI purchased in one of the accounts that are moving or were they purchased in the master payer with sharing turned on. If they are in the accounts moving need to connect with Nathan and understand how those move and if the RIs need to be added into the sharing pool. 7/16 PJC - complete w/findings - Jason to confirm remediation Prod not yet moved? Found though invoice email: Advance health- AWS: ****0485 -$39.12 - aws-advancehealth@hcentive.com ????? -AWS: ****5742 - $5.45 - tarun@tarun.me; eric.letada@hcentive.com ????? - AWS: ****0680 - $27.90 - aws-xpg-prod@hcentive.com | Y | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
HealthMarkets | UHC | UHC E&I | Joe Waggoner | Marie Stodolka | Tony Turner | Mike Britain | [10 empty] | Y | AWS | [6 empty] | JG: AWS invoice intercept. With Tony and team on 'on-prem' efforts. |  | In Progress | Complete | Complete | Complete | In Progress | [6 empty] | 9/18 - Awairing meeting to schedule to review Cloud process BP requested delay to allow team to address security issues
HealthSCOPE | UHC | UHC E&I | Joe Waggoner | David Strong | Lori Berg | Beasley, Tim [From HSB] <Tim.Beasley@healthscopebenefits.com |  | Yes | [8 empty] | Y | AWS | [6 empty] | 3rd party, Deerwalk, provides data warehousing functionality by hosting the functionality on Azure public cloud services where Deerwalk holds/owns the subscription/account with Microsoft vs HealthScope |  | No Cloud Workloads | Complete
Humedica | Optum | OptumInsight | Angela Thorpe | Ann Gerity | none | Sean Castruita Mike Mulhern |  |  | 2020-07-23 | 2020-08-26 |  |  |  | Yes |  |  | Y | AWS |  |  | 40000 |  |  | NA | 9/8 AG - account numbers requested last week from Patrica, response pending 8/26 AG - Response from Patricia Jordan re cloud presence below, all accounts are Optum accounts managed by HCC today: 1. Do you have a workload (not O365) running in a Public Cloud provider? (Ex: Database, application, other cloud services) a. If you have public cloud presence, which providers? (Ex: AWS, Azure (not O365), GCP) Provider Analytics currently does have AWS presence (Optum Performance Analytics), which includes applications, EC2 and Redshift. This would be the only workload we have that would have come from the Humedica acquisition. 2. Do you utilize a 3rd party to administer/facilitate/resell public cloud services? a. If 3rd party is used, is there a contract in place? Expiration date? We do not use a 3rd party. HCC manages the overall relationship with AWS and Azure 3. Do you utilize Microsoft O365? For our teams, yes. 4. Does the business partner know their approximate monthly spend for their public cloud workload? Current monthly spend is about $40k. 8/25 AG - Mike Mulhern confirmed a legacy cloud instance was owned by Advisory Board (they have completed migration in to Optum), they are using a commercial cloud solution for flagship OPA product. 7/23 AG - identifed point of contact, enagaged for status |  | Complete | Complete | Complete | Complete | Complete | Validating
Lewin | Optum | OptumInsight | Angela Thorpe | Ann Gerity | none | Brad Harrison, Jeff Hockett |  | No | NA | NA | NA | NA |  | Yes |  |  | Y | Azure | [6 empty] | 9/8 update: Lewin is bound by government contracts, cannot integrate. They have requested best practice/diagrams for construction of their O365 tenant. 8/25 AG - Lewin is already working with Optum on the O365 migration plans. I don't believe any additional action is needed. 7/28 AG - no integration in scope. No additional action will be taken unless otherwise directed by HCC. 7/23 AG - from Brad Harrison, BP: Lewin is currently working with Optum on our O365 tenant and migration plans. We also have a project team that have setup an Azure Tenant to support a project. It’s in the early stages and my team is just getting access to it. I believe it’s just a single VM at the moment. It’s part of COVID work for a client so urgency is the push. Would like to know if you have any information about cloud standards and processes you have in place. I don’t believe we can migrate any items to Optum as we are an NIE with OCI and compliance issues. We have been owned by UHG/Optum over 13 years and our integration status has not changed over the years because of those issues. Right now, no UHG/Optum employee can have any access to any of our systems according to our government contracts. It’s not really an IT issue but legal and compliance. |  | No Cloud Workloads | Complete
Logistics Health, Inc. | Optum | OptumInsight | Angela Thorpe | Ann Gerity | none | Renae Teale |  |  | 2020-07-23 | 2020-08-26 |  |  |  | No |  |  | Y | [6 empty] | NA | 8/27 AG - response from Joe Molitor: Some of our contracts (Government/Military) do not allow us to leverage cloud services without extensive reviews and amending the boundaries of our compute environment. Specific items that validation was provided for: workload running on public cloud, 3rd party to administer/facilitate/resell public cloud services, Misrosoft O365, monthly chargebacks (if applicable) - response to all was NO 8/25 - engaged with Joe Molitor to address initial questions provided by Jeff to validate what actions if any are needed. 7/28 AG - there was limited integration with LHI, federal contacts prohibit access into LHI. Will confirm if there is cloud presence. 7/23 AG - identifed point of contact, engaged for status |  | No Cloud Workloads | Complete
Lusiadas Saude | UHC | UHC Global | Thomas Morning | N/A | Paul Kocon | [11 empty] | TBD | [9 empty] | Not Started | Not Started | [9 empty] | Evaluating international regulations, effort, timing, and impact
MARCH Vision Care | UHC | UHC E&I | Joe Waggoner | Marie Stodolka | Lori Berg | Shahzad, Shaukat <Shawn.Shahzad@uhc.com | [10 empty] | TBD | [9 empty] | No Cloud Workloads | Complete
MedExpress | Optum | OptumHealth - Care Delivery | Tony Kranz, Alan Kroth | Joanne Castillo | Paul Kocon | Sitnica, Adi <adi.sitnica@medexpress.com>, Metheny, Mike [From MedExpress] <mmetheny@medexpress.com>, Heizler, Mark <mark.heizler@medexpress.com> | 2 |  | 2020-07-17 | Complete 9/9/2020 | 100% | N/A |  | Yes |  |  | Y | AWS |  | GL: 49120-07680-635616 | 34000 | N |  | 876295643570 - Master 829431208957 - Prod - Trans (VPC) 033910624459 - IAM 777984935283 - LOG ------- 253537545995 - Legacy | 1/27: Marketplace blocker has been removed 12/8 - LP team is reporting other priorities came up moving the marketplace analysis and changes into future sprints. Medexpress will not be able to move before end of year 2020. 11/2 - Met with Medexpress, went through their account and their marketplace usage is a conflict for moving the accounts over. Reached out to Laucnhpad team to make a change to allow for their marketplace services in use to work after accounts moved over. 10/2 - Met with Medexpress and they believe their account couldn't move due to them no meeting the terms of the OPtum EA. Jason Validated with AWS Brian A that if there was an issue with the account it would not be covered but doesn't exclude their accounts from moving over under our OPtum Master payer 9/13/20 - Met with HCC and CRIS 9/9 to explain HCC process. Jason L. will follow up. 8/25/20 - Jason W. - I've asked Mike and Adi to confirm those are the accounts that actually moved under UHG 8/24/20 - JAW - Did not find any of the accounts numbers listed under UHG. Account numbers contained in questionnaire 8/17/20 -Jason W. - Daniel Farrah confirms one account already under UHG umbrella, apps in other one will be migrated to Optum data center then account will be closed. 8/8/20 - Jason W. -- Joanne meeting with MedExpress 8/10 to determine needs 7/20/20 Jason W. - Per Adi Confirmed the below. Will follow up with Alan K. and HCC team on next steps. accounts found through invoice capture. Alex to reach out to customer and have initial discussion. Contact on both accounts CorpInvoice@medexpress.com Contact on 876295643570 Mohar, Kimberly [From MedExpress] <kimberly.mohar@medexpress.com> Contacts on 253537545995 Farrah, Daniel [From MedExpress] <daniel.farrah@medexpress.com> Kimberly.Donkin@medexpress.com 7/16 PJC - start discussion w/CRIS |  | In Progress | Complete | Complete | Complete | Complete | In Progress |  |  |  | In Progress |  | 1/27: Marketplace blocker has been removed
MedSynergies | Optum | OptumInsight | Angela Thorpe | Ann Gerity | none | Kirk Shankle Greer Rios |  |  | 2020-07-23 |  |  |  |  | No |  |  | N | [7 empty] | 9/9 AG - Greer provided the update that all accounts have been migrated. She has moved on to another role, will confirm a new point of contact. 9/8 AG - second reach out to Greer, will escaalte by EOD if no response. 8/27 update AG - idenfied Greer Rios as a point of contact, reached out for details in public cloud presence. 7/28 - point oc contact no longer with company, looking for an alternate point of contact. |  | No Cloud Workloads | Complete
Monarch | Optum | OptumHealth - Care Delivery | Tony Kranz, Alan Kroth | Joanne Castillo | none | Semnanian, AmirAli <ASemnanian@mhealth.com> | 2 | No | 2020-07-17 | Complete 8/12/2020 |  |  |  |  | Yes |  | Y | Azure |  | UHGWM110-026011 |  |  |  | e48c4b41-119f-4eec-8114-cb565eef3b98 (Non-prod) - Verified in UHG | 8/26 - JAW - Verified non-prod account is under UHG - e48c4b41-119f-4eec-8114-cb565eef3b98 7/17 JAC - Per Amir, no cloud presence in Production and no direct subscription with any Cloud vendor. Non-prod in Azure per Bryan N. |  | Complete | Complete | Complete | Complete | Complete | Complete | Complete |  |  | In Progress |  | O365 Migration - Tentative completion end of March
N. American Medical Management (CA) | Optum | OptumHealth - Care Delivery | Tony Kranz, Alan Kroth | Joanne Castillo | Greg Fritz | Greg Prieto, Rick Garcia, greyes@nammcal.com, Jambugeswaran Sakthivel, mpowley@nammcal.com | 2 | No | 2020-07-17 | Complete 8/7/2020 | 100% | N/A | N/A | N/A | N/A | N/A | N |  | N/A | N/A | 0 | N/A | N/A | N/A | 08/07/20 Jason W - Aha is cloud based software, no public cloud hosting per Mark P. No HCC needed at this time. 7/23/20 Jason W - Per Mark Powley, currently using Aha, will follow up. | Y | No Cloud Workloads | Complete
National MedTrans | UHC | UHC E&I | Joe Waggoner | David Strong | none | Mark Warburton & Syed Amir |  | No | Complete |  |  | Complete |  | Complete | Complete | In Progress | Y | AWS | Complete | Complete | 221000 | N | N/A | 741927687585 | AWS Org migration schedule 5/1 4/6- filed Existing account migration form. Jeff/Jason met with medtrans to get the processing moving forward. Waiting on ASK ID with GL mapped to begin forward movement. Jeff: Jeff, Heather, Carissa, and Todd, determined no action at this time. Jeff: Meeting w/ Syed Amir 11/7. Follow-up 7/12 7/16 PJC 10 violations to complete - divested - call complete Divestiture of National MedTrans is underway | Y | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
New West Physicians | Optum | OptumHealth - Care Delivery | Tony Kranz, Alan Kroth | Joanne Castillo | Ashish Palia | Joe Hajek | 2 | No | 2020-07-17 | Complete 7/17/2020 |  |  |  |  | Yes |  | Y | Azure | [5 empty] | 3a28f36e-e4d4-4695-82ab-5f90e5874757 | 7/17 JAC - Per Joe Hajek/NWP, public cloud migration is complete. | Y | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete |  | Complete
Optum Brazil | Optum | Optum International | Thomas Morning | N/A | none | [11 empty] | Y | [9 empty] | Not Started | Not Started | [9 empty] | Evaluating international regulations, effort, timing, and impact
Optum Workers’ Comp | Optum | Optum Rx | Angela Thorpe | Chris Bongartz |  |  |  |  | 2020-08-25 | 2020-08-25 | 100% | Complete 7/23/2020 | N/A | N/A | N/A | N/A | N |  | N/A | N/A | NA | N/A | N/A | N/A | 0825/20 Jason W. - Per Colm Hasson, nothing currently hosted in Azure or AWS PJC 7/23 - Reviewed the deck w/Chad Mines & Chris Bongartz |  | No Cloud Workloads | Complete
OptumCare NV - 4C Medical Group | Optum | OptumHealth - Care Delivery | Tony Kranz, Alan Kroth | Joanne Castillo | Kevin McCormick | Dave Tornell | 2 | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N |  | N/A | N/A | N/A | N/A | N/A | N/A | 7/20 - JAC - Per Dave Tornell/4C, no public cloud presence. |  | No Cloud Workloads | Complete
OptumCare NV - Radiation Oncology of NV (USONV) | Optum | OptumHealth - Care Delivery | Tony Kranz, Alan Kroth | Joanne Castillo | none |  | 2 | [9 empty] | N | [9 empty] | No Cloud Workloads | Complete
OptumCare NV - Southwest Medical Associates | Optum | OptumHealth - Care Delivery | Tony Kranz, Alan Kroth | Joanne Castillo | none |  | 2 | [9 empty] | N | [9 empty] | No Cloud Workloads | Complete
OrthoNet | Optum | Optum Consumer Solutions | Tedd Mendes |  | none | [11 empty] | TBD | [9 empty] | No Cloud Workloads | Complete
Peoples Health | UHC | UHC M&R | Joe Waggoner | Marie Stodolka | Heather Taylor | [11 empty] | TBD | [9 empty] | No Cloud Workloads | Complete
PlusOne | Optum | Optum Consumer Solutions | Tedd Mendes |  | none | [11 empty] | TBD | [9 empty] | No Cloud Workloads | Complete
POMCO Group | UHC | UHC E&I | Joe Waggoner | Marie Stodolka | none | [11 empty] | TBD | [9 empty] | No Cloud Workloads | Complete
ProHEALTH Care (NY) | Optum | OptumHealth - Care Delivery | Tony Kranz, Alan Kroth | Joanne Castillo | Beth Lowicki | Babu Kaduraali, Kelly Katchis | 2 | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N |  | N/A | N/A | N/A | N/A | N/A | N/A | 7/28 Jason Williams - Per Babu K, no public cloud presence. | Y | No Cloud Workloads | Complete | [7 empty] | Not Started
ProHealth Physicians (CT) | Optum | OptumHealth - Care Delivery | Tony Kranz, Alan Kroth | Joanne Castillo | Beth Lowicki | Loreene Flebeau and Elizabeth Thornquist | 2 | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N |  | N/A | N/A | N/A | N/A | N/A | N/A | 7/17/20 Jason W. - Per BetsyTornquist, no public cloud | Y | No Cloud Workloads | Complete | [7 empty] | In Progress
Quality Software Services, Inc. | Optum | OptumInsight | Angela Thorpe | Ann Gerity |  | Peter Tan Derek dela Noche Adhikarapatti, Venugopalan [From QSSI] <vadhikarapatti@qssinc.com> procurement@qssinc.com Managed Services [From QSSI] <ms@qssinc.com> |  | No | 2020-07-23 |  |  |  |  | No |  |  | Y |  |  |  | 320 |  |  | 293968997653 965593199775 | 9/8 AG - QSSI is bound by the same government contracts as Lewin (all of OptumServe falls into this category). They cannot integrate with Optum. O365 is not currently in use, they are considering the O365 suite without cloud drive or cloud data storage. 8/25 AG - I reached out to Peter Tan to confirm if they are on O365 in the cloud. 8/7 AG - entity is minimally integrated, goverment contracts are managed and Optum cannot access/own accounts. No additional action will be taken unless directed by HCC. 7/23 AG - identifed Peter Tan as point of contact, reached out for status |  | In Progress | Complete | [9 empty] | 9/18 - Discuss approach with HCC team
QualityMetric | Optum | OptumInsight | Angela Thorpe | Ann Gerity | Kevin Joslyn |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | N |  | NA | NA | NA | NA | NA | NA | 8/26 AG - email is hosted in prem. No additonal action will be taken. 7/21/2020 AG - no public cloud presence |  | No Cloud Workloads | Complete
Radiation Oncology Center of NV | Optum | OptumHealth - Care Delivery | Tony Kranz, Alan Kroth | Joanne Castillo | Greg Fritz | Schatz, Curt <curt.schatz@optum.com> |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N |  | N/A | N/A | 0 | N/A | N/A | N/A | 7/22/2020 Jason W. - Curt S. confirmed no public cloud | Y | No Cloud Workloads | Complete | [7 empty] | Not Started
Rally Health | Optum | Optum Consumer Solutions | Tedd Mendes |  | none |  | 1 | [6 empty] | Blocked | Blocked | Blocked | Y | ? | Blocked |  | 806000 |  |  | 900901929911 (Payer) 438528284888 892514608735 738699725475 144137586169 841246781991 585595130751 374434590507 | 7/16 PJC SrEx Ldrsp discussion needed at Franke level |  | In Progress | Complete | Complete | Complete | In Progress |  |  |  |  | Not in Scope |  | 9/21 - Meeting with Tedd Mendes to walk through process for Cloud discovery
Reliant Medical Group | Optum | OptumHealth - Care Delivery | Tony Kranz, Alan Kroth | Joanne Castillo | none | Richard Morel and Paul Nichols | 2 | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N |  | N/A | N/A | N/A | N/A | N/A | N/A | 7/17 JAC - Per Paul Nichols/RMG, no public cloud presence. | Y | No Cloud Workloads | Complete | [7 empty] | Not Started
Rocky Mountain Health Plan | UHC | UHC C&S | Joe Waggoner | David Strong | Satyendra Kumar | Nandan Menon Ed Frederick |  | No | Complete |  |  | Complete |  | Complete | Complete | Complete | y | Azure | Complete |  | 5000 |  |  | 7e510e08-8b69-4de5-8a95-f90aecba9346 | 8/25 TT : Workload has migrated to Optum Tenant 1/2 - email sent to Ed to validate Tenant decommissioned. 12/13- emailed to verify Tennant decom 7/16 PJC complete | Y | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
UHG R&D - AWS | UHG | UHG Corporate | Tedd Mendes | Jason Williams | Paul Kocon | Kristy Stasik - kristy.stasik@optum.com (Product) Frank Markson - frank.markson@uhg.com | 1 |  | Hold pending Ex Leadership discussions |  |  |  |  | Blocked | Blocked | Blocked | Y | AWS | In Progress |  | 33000 |  |  |  | Jason to follow up with Frank on the AWS account 2/14 Atia: SavvySherpa's network integration was schedule complete in Q4 2019. SavvySherpa used a 3rd party to provide and maintain HITRUST certification of their AWS environment. SavvySherpa uses AWS, Azure and Google Cloud. Contact security team has are Erik Edvalson 1/28: Jeff following up with Kristy 7/16 PJC - Political discussion required (Franke level) |  | In Progress | Complete | In Progress | [6 empty] | Not in Scope |  | 9/21 - Meeting with Tedd Mendes to walk through process for Cloud discovery
UHG R&D - Azure | UHG | UHG Corporate | Tedd Mendes | Jason Williams | Paul Kocon | Kristy Stasik - kristy.stasik@optum.com (Product) Frank Markson - frank.markson@uhg.com | 1 |  | Hold pending Ex Leadership discussions |  |  |  |  | Blocked | Blocked | Blocked | Y | Azure | In Progress |  | 33000 |  |  |  | Jason to follow up with Frank on the AWS account 2/14 Atia: SavvySherpa's network integration was schedule complete in Q4 2019. SavvySherpa used a 3rd party to provide and maintain HITRUST certification of their AWS environment. SavvySherpa uses AWS, Azure and Google Cloud. Contact security team has are Erik Edvalson 1/28: Jeff following up with Kristy 7/16 PJC - Political discussion required (Franke level) |  | In Progress | Complete | In Progress | [6 empty] | Not in Scope |  | 9/21 - Meeting with Tedd Mendes to walk through process for Cloud discovery
UHG R&D - Google | UHG | UHG Corporate | Tedd Mendes | Jason Williams | Paul Kocon | Kristy Stasik - kristy.stasik@optum.com (Product) Frank Markson - frank.markson@uhg.com | 1 |  | Hold pending Ex Leadership discussions |  |  |  |  | Blocked | Blocked | Blocked | Y | Google | In Progress |  | 33000 |  |  |  | Jason to follow up with Frank on the AWS account 2/14 Atia: SavvySherpa's network integration was schedule complete in Q4 2019. SavvySherpa used a 3rd party to provide and maintain HITRUST certification of their AWS environment. SavvySherpa uses AWS, Azure and Google Cloud. Contact security team has are Erik Edvalson 1/28: Jeff following up with Kristy 7/16 PJC - Political discussion required (Franke level) |  | In Progress | Complete | In Progress | [6 empty] | Not in Scope |  | 9/21 - Meeting with Tedd Mendes to walk through process for Cloud discovery
Southwest Medical Associates | Optum | OptumHealth - Care Delivery | Tony Kranz, Alan Kroth | Joanne Castillo | none | Verchick, Tami <Tami.Verchick@optum.com> |  |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N |  | N/A | N/A | 0 | N/A | N/A | N/A | 7/22/2020 Jason W. - Tami Verchick confirmed no public cloud | Y | No Cloud Workloads | Complete | [7 empty] | Not in Scope
Student Resources | UHC | UHC E&I | Joe Waggoner | Marie Stodolka | none |  |  |  |  | 2020-09-01 | 100 | [5 empty] | N | [9 empty] | No Cloud Workloads | Complete
Surgical Care Affiliates - AWS | Optum | OptumHealth - Care Delivery | Tony Kranz, Alan Kroth | Joanne Castillo | Greg Fritz | Willcox, James <James.Willcox@scasurgery.com> Bodden, Mark E [From SCA] <Mark.Bodden@scasurgery.com> Ajay.Kambhampati@scasurgery.com |  |  | 44026 | Complete 7/14/2020 | 100 | N/A | Complete | Yes | Postponed |  | Y | AWS | Postponed | UHGWM110-026385, GL: 47300-619700-07685 | 7000 |  |  | Azure Tenant Dev/Test -c1abffaf-fc5e-4ed1-9959-d7c44aecf63a Prod f0f50638-bede-4f1e-87fc-a1e751da3d74 AWS PWC is initially creating, and will transition-in 944607642796 | 8/26/20 - Jason W. -- followup with Ajay on HCC questions: 1) The AWS/PWC connection is actually a solution built by PWC, hosted in SalesForce, with call center handled via AWS Connect. It’s going live Sept. 1. SCA is already engaged with Optum’s SF team (architect from Optum is Nick Burton) and this is already within Optum’s SF account. Nothing else hosted in AWS 8/8/20 Jason W. - discussed with Bryan N. and Jason L. Transition already in progress, no need for walking deck presentation. 7/22/2020 Jason W. - Nieznajko, Bryan J <bryan_nieznajko@optum.com> working with Ajay, will follow up Care Delivery Organization, NIE Hefty Azure AD, SCA Surgery will remain on their own tenancy. Working on ASKID/GL, UHG owner. Have identified that the Launchpad policies applied to the tenant would break some of the services running in the subscription. Cannot apply launchpad to the tenant/subscription until those are remediated. 7/14 - Joanne Castillo - Met with SCA, HCC, CRIS, EIS. Determined work in flight with PWC for AWS Connect. Parallel efforts: a)normal net new workload intake on the cloud.optum.com b) discovery work to migrate the workload being stood up to the UHG tenant. |  | In Progress | Complete | Complete | Complete | Complete | Complete | In Progress | In Progress
Surgical Care Affiliates - Azure | Optum | OptumHealth - Care Delivery | Tony Kranz, Alan Kroth | Joanne Castillo | Greg Fritz | Willcox, James <James.Willcox@scasurgery.com> Bodden, Mark E [From SCA] <Mark.Bodden@scasurgery.com> Ajay.Kambhampati@scasurgery.com |  |  | 2020-07-14 | Complete 7/14/2020 | 100 | N/A | Complete | Yes | Postponed |  | Y | Azure | Postponed | UHGWM110-026385, GL: 47300-619700-07685 | 7000 |  |  | Azure Tenant Dev/Test -c1abffaf-fc5e-4ed1-9959-d7c44aecf63a Prod f0f50638-bede-4f1e-87fc-a1e751da3d74 AWS PWC is initially creating, and will transition-in | 12/15: LaunchPad ticket created to resolve issues with migrating Azure. Launchpad has move resolution to Q1,2021 8/26/20 - Jason W. -- followup with Ajay on HCC questions: 2) SCA is running Office 365 and last year when they renewed it came under the UHG/Optum account 3) There are some critical workloads hosted in Azure and SCA has engaged with Jason Lahr on these, but they hit the pause button to sort out how to extricate these workloads from their O365 tenant. SCA currently has a prod and test subscription to Azure 4) SCA has “10 to 15” developers accessing the Azure environments, and “just a few” have MSIDs (no exact count) but none of them have Optum laptops 8/8/20 Jason W. - discussed with Bryan N. and Jason L. Transition already in progress, no need for walking deck presentation. 7/22/2020 Jason W. - Nieznajko, Bryan J <bryan_nieznajko@optum.com> working with Ajay, will follow up Care Delivery Organization, NIE Hefty Azure AD, SCA Surgery will remain on their own tenancy. Working on ASKID/GL, UHG owner. Have identified that the Launchpad policies applied to the tenant would break some of the services running in the subscription. Cannot apply launchpad to the tenant/subscription until those are remediated. 7/14 - Joanne Castillo - Met with SCA, HCC, CRIS, EIS. Determined work in flight with PWC for AWS Connect. Parallel efforts: a)normal net new workload intake on the cloud.optum.com b) discovery work to migrate the workload being stood up to the UHG tenant. |  | No Cloud Workloads | Complete | Complete | Complete | Complete | In Progress
TEC - Northwest Physicians Network | Optum | OptumHealth - Care Delivery | Tony Kranz, Alan Kroth | Joanne Castillo | Farhan MO | Kyle.Getz@the polyclinic.com john.sargent@polyclinic.com | 1 | [9 empty] | Y | Azure |  | UHGWM110-026942 (NPN) |  |  |  |  | 1/27/21: consolidating accounts to NPN. Migration is expected to complete by end of February |  | In Progress | Complete | Complete | Complete | Complete | In Progress |  |  |  | Not Started |  | 1/27/21: consolidating accounts to NPN. Migration is expected to complete by end of February
TEC - The Everett Clinic | Optum | OptumHealth - Care Delivery | Tony Kranz | Joanne Castillo | Annaliese Reutemann | Gary Kuyat (Gkuyat@everettclinic.com) Chuck Morrenzin (cmorrenzin@everettclinic.com) Jason Rice (jrice@everettclinic.com) Kevin Buretta (kburetta@everettclinic.com) | 1 |  | 2020-07-17 | Complete 8/26/2020 | 85% | N/A | Complete 9/18/2020 | No |  |  | Y | Azure |  | UHGWM110-027296 | 1600 | Yes | Ascension | EveretteClinic Azure Tenant - No Azure Subscription NPN (Northwest Physicians Network) Azure Tenant - Has an Azure subscription TEC Tenant - Has an Azure subscription | 12/15: LaunchPad ticket created to resolve issues with migrating Azure. Launchpad has move resolution to Q1,2021 EverettClinic Tenant Has EA which expires 6/30/2020. o Office 365  John flood handling the license o PowerBI Pro  John flood handling the license o MFA, Azure AD enabled and utilization  Need to understand if this can be moved into our EA as an account, what would the billing do. NPN (Northwest Physicians Network) Tenant No EA, Month to Month o Exchange, email migrated to TEC tenant completed o Sharepoint (migration in process to TEC) o Teams (migrate to TEC, will go along with SharePoint) o Website (in an Azure Subscription)  No ties to SharePoint Need to check with Uriah, can admin/developers Identity by synced with OptumCare tenant TEC Tenant Need to check with John Flood on what the expectation is, tenant remains and moves over or everything migrated off of the tenant. 7/14 - Joanne Castillo - Scheduling discovery meeting with TEC, John Flood and Jason Lahr. Action: 1. Determine how MFA runs/works. If part of a subscription, then discuss moving over to under one of our other tenants. This would be done by someone at TEC sharing screen and running thru the MFA use case. 2. For the other two tenants, determine final intended disposition. For example will they migrate over to UHG tenant. We would need to have the walking deck ready to discuss what that would mean. 3. Possible follow-up is to work with/include Uriah Norris regarding how TEC identities can be synced with our OptumCare tenant. 7/30 JAC - Meeting to review walking deck requires rescheduling due to conflict for TEC. Complete discovery form prior to rescheduling per HCC team. 8/6 JAC - HCC Overview (walking deck) meeting rescheduled from 8/18 to 8/20 due to conflict for TEC. 8/25 JAC - Key Updates: 1) Discovery questionnaire completed 8/11 2) Walking deck review scheduled 8/20 - not needed per BP (stated during meeting) 3) Discovery questionnaire reviewed 8/20 and 8/25 - further discussion required - continuing 8/26 8/26 JAC - Additional Discovery review session complete. BP to provide ASK ID. If valid, hand off to HCC team (HCC ready). 9/18 JAC - ASK form submitted directly in ASK by Bryan N. ASK ID# TBD. 9/24 JAC - ASK ID for NPN created. Additional ASK reg required for TEC. |  | No Cloud Workloads | Complete | Complete | Complete | Complete | In Progress |  |  |  | Not Started
TEC - The Polyclinic | Optum | OptumHealth - Care Delivery | Tony Kranz, Alan Kroth | Joanne Castillo | Farhan MO | Kyle.Getz@the polyclinic.com john.sargent@polyclinic.com | 1 |  | 2020-07-17 | Complete 8/12/2020 | 100% | N/A | N/A | No | N/A | N/A | O365 Only |  | N/A | N/A | N/A | N/A | N/A | N/A | 08/12/20 Jason W. -- after meeting with TPC, confirmed Azure is only tied O365 tenant. No TPC apps are in a public cloud hosting environment. Nothing for HCC at this time. 08/08/20 Jason W. -- meeting with TPC 8/10 to complete questionnaire, review deck if needed 07/20/20 Jason W. - confirmed with Kyle G. can't start until current contract expires 11/30 MS contract in place - cannot benefit from our discount until late November 7/16 PJC - Jeff G email contract w/MS and can't bend until November. Need to follow up w/Jacob Palen w/ ES&P | Y | No Cloud Workloads | Complete | [7 empty] | Not Started
UHG Brazil (AMIL) | UHC | UHC Global | Thomas Morning | N/A | none | [11 empty] | Y | [9 empty] | Not Started | Not Started | [9 empty] | Evaluating international regulations, effort, timing, and impact
UnitedHealthcare Nevada Market | UHC | UHC E&I | Joe Waggoner | Marie Stodolka | none | [11 empty] | TBD | [9 empty] | No Cloud Workloads | Complete
USHEALTH Group | UHC | UHC E&I | Joe Waggoner | Marie Stodolka | Bryan Gastonguay | Nathan Staub - USHealth Group | [10 empty] | Y | Azure |  |  | 30000 | Y | PCM/Insight is the reseller, however we administer it our tenant in house. |  | Per Nathan Staub - Azure and O365 Other hosted services like Box, Fuze, Five9, LogicMonitor, Atlassian, Cloudflare, Citrix in use 2/10- emailed Sonja on if AWS exist and who owns. |  | In Progress | Complete | Complete | Complete | Complete | In Progress |  |  |  | Not Started |  | 9/18 - Awaiting meeting to schedule to review Cloud process
USMD Health System | Optum | OptumHealth - Care Delivery | Tony Kranz, Alan Kroth | Joanne Castillo | Beth Lowicki | Steve Miller (PM), Mike Wester | 2 | No | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N |  | N/A | N/A | N/A | N/A | N/A | N/A | 7/22 JAC - Per Bryan Nieznaiko/OCIO, no public cloud presence. | Y | No Cloud Workloads | Complete | [7 empty] | Complete
Vivify Health - AWS | Optum | OptumInsight |  |  | Ashish Palia | Alan Stryker <a.stryker@vivifyhealth.com> Palia, Ashish R <ashish.palia@optum.com> | [8 empty] | Complete w/ Findings |  | Y | AWS | Complete | UHGWM110-024813 | TBD |  |  | -AWS (NonProd)single account 492565762323 - move to HCC | AWS Org migration scheduled 4/28 4/23- filed SN form to have record created meeting 3/24 - request to get GL mapped encountered some back and forth with finance, Ashish is working through it Meeting 3/12 - ASK ID exists with no GL. finance contact provided with instructions how to get GL updated. UHGWM110-024813 CENTRILOGIC (can't move out) - for Canada has to remain in CA ARMOR (still has 2 year contract w/ them) - for US (located in Tx and Az) AWS - is all development work (separated from Prod (EC2, Lambdas, S3, CloudFront, .) 7/16 PJC - complete 7/16 w/ all remediation complete Azure (NonProd) Tenant & single sub running a single VM for DLP (running O365) this will go away, It can not be decomed until the mailboxes are moved over. Office365 and mail migration team has the action. AWS (NonProd)single account 492565762323 - move to HCC Armor: (Prod) US workloads under contract /DCs (still has 3 yr contract)(no action) Centri Logic: Canada workloads under contract /DCs (no action) |  | In Progress | Complete | Complete
Vivify Health - Azure | Optum | OptumInsight |  |  | Ashish Palia | Alan Stryker <a.stryker@vivifyhealth.com> Palia, Ashish R <ashish.palia@optum.com> | [8 empty] | Complete w/ Findings |  | Y | Azure | Complete | UHGWM110-024813 | TBD |  |  | -AWS (NonProd)single account 492565762323 - move to HCC | 12/15: More discovery is needed to determine how ClearWays is managing the cloud. Tedd Mendes will schedule meeting with Vivify resource AWS Org migration scheduled 4/28 4/23- filed SN form to have record created meeting 3/24 - request to get GL mapped encountered some back and forth with finance, Ashish is working through it Meeting 3/12 - ASK ID exists with no GL. finance contact provided with instructions how to get GL updated. UHGWM110-024813 CENTRILOGIC (can't move out) - for Canada has to remain in CA ARMOR (still has 2 year contract w/ them) - for US (located in Tx and Az) AWS - is all development work (separated from Prod (EC2, Lambdas, S3, CloudFront, .) 7/16 PJC - complete 7/16 w/ all remediation complete Azure (NonProd) Tenant & single sub running a single VM for DLP (running O365) this will go away, It can not be decomed until the mailboxes are moved over. Office365 and mail migration team has the action. AWS (NonProd)single account 492565762323 - move to HCC Armor: (Prod) US workloads under contract /DCs (still has 3 yr contract)(no action) Centri Logic: Canada workloads under contract /DCs (no action) |  | In Progress | Complete | Complete
WellMed | Optum | OptumHealth - Care Delivery | Tony Kranz, Alan Kroth | Joanne Castillo | Kevin McCormick | Joseph Trudell - jtrudell@wellmed.net, Daniel Moore, Mouda Lee, Simon Castillo, Manuel Salinas | 2 |  | 2020-07-17 | Complete 8/12/2020 | 0.2 | Scheduled 8/28/2020 |  | No | Initial Outreach |  | N | [6 empty] | 145020174949 | JAW - No Public Cloud - running AzurePack/AzureStack on-prem AE accounts found through invoice capture. Alex to reach out to customer and have initial discussion. thedevelopmentbox@wellmed.net Trudell, Joseph [From WellMed] <JTrudell@wellmed.net> JAC - Meeting held with WellMed 8/10 for Discovery. Clarification needed on questionnaire items. Follow up to be scheduled for deck walkthrough and remaining discovery. JAC - Follow up session to complete Discovery scheduled 8/28. |  | No Cloud Workloads | Complete | [7 empty] | In progress
Westmed Practice Partners | Optum | OptumInsight | Angela Thorpe | Ann Gerity | Greg Fritz | Omar Lee |  | No | NA | NA | NA | NA | NA | NA | NA | NA | Y |  | NA | NA | NA | NA | NA | NA | 8/25 AG - WestMed has engaged Optum for help with best practices and migration support but we did not acquire them so they will not integrate with Optum. 7/24 AG - not acquired by Optum, Westmed will own cloud licences. No additional action will be taken unless otherwise directed by HCC. 7/23 AG - IL (Greg Fritz) will confirm public cloud presence with BP |  | No Cloud Workloads | Complete
Insphere Insurance Solutions Inc | [5 empty] | Accounts Payable 9151 BOULEVARD 26 NORTH RICHLAND HILLS , TX , 76180-5600 , US | [17 empty] | 428909497139 | Intercepted invoice for ~$10,000
Equian LLC | [5 empty] | ATTN: Jacqueline A Gentner 6875 State Rd 144 Greenwood , IN , 46143 , US | [17 empty] | 986226531251 | believed to be the stand alone account listed under the Equian - AWS Entitiy Name.
clinovations |  |  |  |  | alan@clinovations.com <alan@clinovations.com> | ATTN: Sumedha Pradhan 349 Grandview Ave Morgantown , WV , 26501 , US | [17 empty] | 40167123569
Diplomat |  |  |  |  | amazon@diplomat.is <amazon@diplomat.is> | Melissa Schaefer 1600 McConnor Parkway Schaumburg , IL , 60173 , US | [17 empty] | 629350603700
Diplomat |  |  |  |  | ben@8thdaysoftware.com | [18 empty] | acct ending - ****0007
324326102354
HCC GOVT | EEPS |  |  |  |  | Jeff Goedert
Note on H2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Set priority in numeric asending order with 1 being highest priority
Note on J2: Williamson, Jeffrey: Not Started In Progress Complete w/ Date (CRIS)
Note on K2: Patti Connolly: To mark complete w/date the ASK ID, GL, and Cloud Questionnaire completed
Note on M2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not Started Scheduled w/ Date Complete w/ Date (HCC, EIS, CRIS)
Note on N2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: ASKID In Process Awaiting GL assign Complete w/ Date
Note on O2: Williamson, Jeffrey: Record date when entity is ready for HCC team to perform migration. HCC Ready: Discovery complete and business partner is understanding the scope & financial impact Complete w/ Date (CRIS)
Note on P2: Williamson, Jeffrey: Record date when entity tenant(s) has been migrated and LaunchPad applied Not Started In Progress Complete w/ Date (HCC)
Note on Q2: Williamson, Jeffrey: Record date the findings have been remediated, risk review complete usually within 30 days Not Started In Progress Complete w/ Date (HCC/EIS)
Note on S2: Williamson, Jeffrey: Record the public cloud provider Include notation if paying the provider for support (ex: AWS - Support)
Note on X2: Williamson, Jeffrey: Record terms of existing contracts, expiration dates, termination information
Note on Y2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Record account numbers, approx month cost and how the account is used (dev, stage, prod, etc)

## Discovery
Discovery Tracker | 2020-08-14 | 2020-08-21 | 2020-08-28 | 2020-09-04 | 2020-09-11 | 2020-09-18 | 2020-09-25 | 2020-10-02 | 2020-10-09 | 2020-10-16 | 2020-10-23 | 2020-10-30 | 2020-11-06 | 2020-11-13 | 2020-11-20 | 2020-11-27 | 2020-12-04 | 2020-12-11 | 2020-12-18 | 2020-12-25 | 2020-01-01
Program Titan NIEs/Cloud Providers Total# | 23 | 23 | 62 | 71 | 71
Cloud Validation Completed | 15 | 17 | 35 | 45 | 63
No Cloud Workloads | 10 | 10 | 15 | 23 | 30
Previously Migrated | 0 | 0 | 2 | 4 | 12
Phase 2 Discovery needed | 5 | 7 | 9 | 10 | 13
Not Started (UHC Global) | 0 | 0 | 9 | 8 | 8
Delayed | 3 | 3 | 5 | 8 | 8
NIEs Queued for HCC | 0 | 0 | 0 | 2 | 3